HIRE SENSE

PHASE 0 → PHASE 12

Complete A–Z Development & Execution Roadmap

Planning → Product → Web App → AI → Testing → Validation → Deployment → Final Demo

Project objective Build a working, tested and explainable AI-assisted hiring support MVP. HireSense should help recruiters with early screening and help job seekers understand interview-performance improvement areas, while the final hiring decision remains with the recruiter/user.

Planning date: 10 September 2026
Final readiness target: 20 November 2026

# Table of Contents

Phase 0 — Scope, Validation & Product Design

Phase 1 — Application Foundation

Phase 2 — Database & Authentication

Phase 3 — Recruiter Workflow

Phase 4 — Resume AI

Phase 5 — Job–Candidate Matching AI

Phase 6 — Interview Upload & Speech-to-Text

Phase 7 — Interview/Communication Intelligence

Phase 8 — Unified AI Report & Human Review

Phase 9 — Candidate Feedback

Phase 10 — Testing, AI Evaluation & User Validation

Phase 11 — Deployment, Security & Operations

Phase 12 — Final Validation, Evidence & Demo

Master Architecture

Database & API Blueprint

Development Calendar

Risk Register

MVP Definition of Done

Final Team Workflow

# 1. Project Foundation

The supplied HireSense materials describe an early TRL-2 AI-assisted hiring concept. The primary customer side is recruiters/HR teams and hiring managers; the secondary user side is final-year students/job seekers. The core pain areas are recruiter screening, matching, initial screening, interview assessment and candidate comparison, plus job-seeker problems around shortlisting without feedback, interview performance, communication, self-presentation and knowing weaknesses.

The project roadmap emphasizes validation as well as development. It calls for customer discovery, prototype iterations, recruiter testing, technical/ethical evaluation, business-model validation and a working MVP by 20 November 2026.

Source vs engineering decision This document preserves the project's stated problem, users, roadmap and responsible-AI direction. Specific choices such as React, FastAPI, PostgreSQL, JWT, API names, folder structure and scoring weights are recommended engineering implementations, not claims that the source documents mandated those exact technologies.

# 2. Master Phase Map

| Phase | Goal | Deliverable |
| --- | --- | --- |
| 0 | Freeze scope + validate problem | MVP specification, journeys, architecture |
| 1 | Create application foundation | React + FastAPI running |
| 2 | Persistence + access control | PostgreSQL + authentication |
| 3 | Recruiter workflow | Jobs + applications + candidates |
| 4 | Resume intelligence | Structured candidate profile |
| 5 | Matching intelligence | Explainable job–candidate score |
| 6 | Interview processing | Upload + transcription |
| 7 | Interview intelligence | Observable communication/answer metrics |
| 8 | Unified product | Recruiter report + human review |
| 9 | Candidate side | Actionable feedback |
| 10 | Evidence | Testing + AI evaluation + user validation |
| 11 | Operationalize | Deployment + security + monitoring |
| 12 | Finish | Validated MVP + final demo |

# PHASE 0 — Scope, Validation & Product Design

## Objective

Freeze the MVP before serious coding. Confirm the problem, users, workflows, P0 features, risks and measurable success criteria.

## Process

Document the problem and target users.

Map recruiter and candidate journeys.

Prioritize features as P0, P1 and P2.

Write functional and non-functional requirements.

Create wireframes for recruiter and candidate screens.

Design the system architecture and database.

Define AI output schemas before selecting models.

Create customer-interview and validation plans.

Define AI evaluation and responsible-use criteria.

## Technical implementation

Recruiter → Job → Candidate → Resume → Match → Interview → Report → Human Review

Candidate → Profile → Resume → Interview → Feedback → Improvement

## Acceptance criteria

Problem statement is approved.

MVP feature list is frozen.

Two user journeys are documented.

Architecture/database/API plans exist.

Acceptance criteria exist for every P0 feature.

The team can explain exactly what is in and out of V1.

Phase complete when The team can explain exactly what is in and out of V1.

# PHASE 1 — Application Foundation

## Objective

Build the basic web application and prove that frontend and backend communicate before adding AI.

## Process

Create Git repository and project folders.

Set up React with Vite.

Set up FastAPI.

Create a health-check API.

Create React routing.

Build placeholder Login, Register, Recruiter Dashboard and Candidate Dashboard pages.

Connect frontend to backend.

Commit the reproducible starter project.

## Technical implementation

HireSense/

├── frontend/

├── backend/

├── ai/

├── data/

└── docs/

Backend:

python -m venv .venv

pip install fastapi uvicorn sqlalchemy pydantic python-multipart

uvicorn app.main:app --reload

GET /health → {"status":"ok"}

## Acceptance criteria

React runs locally.

FastAPI runs locally.

Frontend can call backend.

Repository is version controlled.

Clean-machine setup is documented.

Phase complete when Clean-machine setup is documented.

# PHASE 2 — Database & Authentication

## Objective

Create persistent data and secure role-based access.

## Process

Install/configure PostgreSQL.

Create users table.

Implement password hashing.

Implement registration.

Implement login.

Issue and validate access tokens.

Protect recruiter and candidate routes.

Add ownership checks for objects/files.

Test unauthorized access.

## Technical implementation

users

-----

id

name

email

password_hash

role

created_at

updated_at

Roles:

RECRUITER

CANDIDATE

ADMIN

Flow:

Register → hash password → save

Login → verify → token

Request → token validation → role/ownership check

## Acceptance criteria

Recruiter can register/login.

Candidate can register/login.

Passwords are never stored in plaintext.

Role permissions work.

Users cannot access unauthorized records.

Phase complete when Users cannot access unauthorized records.

# PHASE 3 — Recruiter Workflow

## Objective

Build the first real business workflow: recruiter creates a job and manages candidates/applications.

## Process

Build recruiter dashboard.

Build create/edit/view job pages.

Create required and preferred skill fields.

Create application records.

Create candidate list.

Create candidate detail page.

Add application statuses.

Add placeholder AI-analysis state.

## Technical implementation

POST /jobs

GET  /jobs

GET  /jobs/{id}

PUT  /jobs/{id}

POST /applications

GET  /jobs/{id}/applications

GET  /candidates/{id}

Job:

title, description, experience

required_skills, preferred_skills

status, recruiter_id

## Acceptance criteria

Recruiter can create a job.

Recruiter can see applications.

Candidate profile can be opened.

Application status can be changed.

No AI is required yet.

Phase complete when No AI is required yet.

# PHASE 4 — Resume AI

## Objective

Convert a candidate PDF resume into structured, job-relevant candidate information.

## Process

Validate file type and size.

Store the original file securely.

Extract PDF text.

Clean and segment the text.

Detect common resume sections.

Extract name, education, skills, experience, projects, certifications and links.

Normalize obvious skill aliases.

Validate AI output against a schema.

Save model/provider/version metadata.

Display structured profile with evidence.

## Technical implementation

PDF → validate → store → extract text → clean

→ section detection → structured extraction

→ skill normalization → candidate profile

Example:

{

"name":"...",

"skills":["Python","SQL"],

"experience":[...],

"projects":[...],

"education":[...]

}

## Acceptance criteria

Valid resumes become structured profiles.

Unreadable/malformed files fail safely.

AI cannot silently invent unsupported experience.

Original resume remains available as evidence.

Candidate can correct missing profile fields.

Phase complete when Candidate can correct missing profile fields.

# PHASE 5 — Job–Candidate Matching AI

## Objective

Compare candidate evidence against defined job requirements and provide an explainable fit score.

## Process

Normalize job requirements.

Separate required and preferred skills.

Match explicit skills.

Compare relevant experience.

Compare project/evidence relevance.

Calculate requirement coverage.

Combine components into a starting score.

Generate evidence-based explanation.

Show missing or unclear requirements.

Allow recruiter review/override.

## Technical implementation

Starting implementation example:

Overall =

0.45 * Skills

+ 0.20 * Experience

+ 0.20 * ProjectEvidence

+ 0.15 * RequirementCoverage

Example:

Python ✓

FastAPI ✓

SQL ✓

Machine Learning ✓

Git ⚠ unclear

Overall = 86%

## Acceptance criteria

Every major score has an explanation.

Matched/missing requirements are visible.

Score is not presented as a hiring decision.

Sensitive attributes are not used.

Recruiter remains responsible for the final decision.

Phase complete when Recruiter remains responsible for the final decision.

Scoring warning The formula above is only a starting engineering design. Validate weights with real users and test data before claiming effectiveness.

# PHASE 6 — Interview Upload & Speech-to-Text

## Objective

Accept interview audio/video, process it asynchronously and produce an analysis-ready transcript.

## Process

Validate supported media formats and size.

Store original media securely.

Extract audio from video where necessary.

Send audio to a speech-to-text component.

Store transcript and timestamps where available.

Track processing status.

Handle failed processing gracefully.

Expose transcript to authorized users.

## Technical implementation

Upload → validate → store → queue

→ audio extraction → speech-to-text

→ transcript → analysis_ready

Statuses:

uploaded → queued → processing → completed

└────────→ failed

## Acceptance criteria

Supported media uploads successfully.

Long-running processing does not block the web request.

Transcript is stored.

Processing failures are visible and recoverable.

Phase complete when Processing failures are visible and recoverable.

# PHASE 7 — Interview / Communication Intelligence

## Objective

Analyze observable communication and answer content rather than attempting psychological or personality judgments.

## Process

Store interview questions explicitly for the MVP.

Segment transcript by question/answer.

Calculate word count.

Count configured filler words.

Calculate filler rate.

Calculate speaking rate when timestamps exist.

Identify long-pause indicators.

Evaluate question-specific relevance.

Evaluate answer structure using a rubric.

Evaluate technical concept coverage where appropriate.

Generate evidence-based improvement suggestions.

## Technical implementation

Example:

Word count: 126

Filler words: 11

Filler rate: 8.7%

Speaking rate: 142 WPM

Long pauses: 4

Relevance: High

Structure: Medium

Technical coverage: High

## Acceptance criteria

Metrics are traceable to transcript evidence.

Feedback is actionable.

No personality, honesty, mental-state or emotion claims are made.

Limitations are visible.

Phase complete when Limitations are visible.

Responsible boundary Do not turn voice, accent, facial appearance or video behavior into claims such as “dishonest”, “not confident”, “aggressive” or “bad personality”. Keep the MVP tied to observable speech/text evidence.

# PHASE 8 — Unified AI Report & Human Review

## Objective

Combine resume, matching and interview evidence into one recruiter-facing decision-support report.

## Process

Create unified report schema.

Combine resume analysis.

Add match components and evidence.

Add transcript/interview metrics.

Add strengths and areas to review.

Add AI limitations.

Add recruiter notes.

Add Shortlist/Hold/Reject human actions.

Log decision-related events.

## Technical implementation

Candidate Report

├── Overview

├── Resume Evidence

├── Match Score

│   ├── Skills

│   ├── Experience

│   ├── Projects

│   └── Requirements

├── Interview

│   ├── Transcript

│   ├── Communication Metrics

│   └── Answer Analysis

├── Strengths

├── Areas to Review

├── AI Limitations

└── Human Review

## Acceptance criteria

One candidate report contains the major evidence.

Recruiter can inspect the reason behind scores.

Recruiter can override/ignore AI output.

Human action is stored.

AI does not automatically hire/reject.

Phase complete when AI does not automatically hire/reject.

# PHASE 9 — Candidate Feedback

## Objective

Create the candidate-facing feedback loop so users understand strengths and improvement areas.

## Process

Create candidate feedback page.

Show interview strengths.

Show improvement areas.

Explain why each issue matters.

Give a specific next action.

Store feedback by interview attempt.

Show improvement history.

## Technical implementation

Feedback:

What went well

→ What can improve

→ Why it matters

→ What to do next

Attempt 1 → filler rate 8.7%

Attempt 2 → filler rate 6.2%

Attempt 3 → filler rate 4.8%

## Acceptance criteria

Candidate sees only their own feedback.

Feedback is understandable.

Feedback is actionable.

Feedback avoids personality/psychological labels.

Phase complete when Feedback avoids personality/psychological labels.

# PHASE 10 — Testing, AI Evaluation & User Validation

## Objective

Produce evidence that the software works and that AI outputs are sufficiently reliable for the intended prototype use.

## Process

Write unit tests.

Write API/integration tests.

Test file uploads and failure paths.

Build a fixed evaluation dataset.

Evaluate resume extraction.

Evaluate matching against human references.

Evaluate transcription error.

Evaluate interview analysis against human ratings.

Run usability testing.

Collect structured user feedback.

Run responsible-AI and bias checks.

Document failure cases and improvements.

## Technical implementation

Evaluation set:

50+ AI analysis test cases

30+ human-vs-AI comparison cases

Useful metrics:

- field accuracy / precision / recall / F1

- human–AI agreement

- transcription error / WER

- usefulness/satisfaction rating

- processing time / failure rate

## Acceptance criteria

50+ AI test cases are documented.

30+ human-vs-AI comparison cases are documented.

At least 10 prototype users test the system.

15+ pilot users are targeted/validated according to the roadmap.

Major usability issues are recorded and addressed.

Ethical-risk assessment is documented.

Phase complete when Ethical-risk assessment is documented.

# PHASE 11 — Deployment, Security & Operations

## Objective

Move the tested MVP from a laptop to a reproducible demo/staging environment.

## Process

Containerize services where practical.

Configure managed or hosted PostgreSQL.

Deploy backend.

Deploy frontend.

Configure secure object/file storage.

Configure background worker.

Set environment variables/secrets.

Enable HTTPS.

Add monitoring and logs.

Test backup/recovery and deployment instructions.

## Technical implementation

Internet

↓

React Frontend

↓ HTTPS

FastAPI Backend

├── PostgreSQL

├── File/Object Storage

└── AI/Worker Services

Environment:

DATABASE_URL=...

JWT_SECRET=...

STT_API_KEY=...

LLM_API_KEY=...

VITE_API_BASE_URL=...

## Acceptance criteria

Deployment can be reproduced.

Secrets are not committed to Git.

HTTPS is enabled.

Authorization works in deployed environment.

AI/background failures are visible.

Demo flow works from a fresh account.

Phase complete when Demo flow works from a fresh account.

# PHASE 12 — Final Validation, Evidence & Demo

## Objective

Freeze the evidence-backed MVP and prepare the final demonstration.

## Process

Freeze code version.

Run the full regression suite.

Run the complete recruiter demo.

Run the complete candidate demo.

Update KPI dashboard with actual values.

Finalize AI evaluation report.

Finalize user-testing evidence.

Finalize responsible-AI assessment.

Document known limitations.

Deploy final demo environment.

Prepare presentation and backup demo data.

## Technical implementation

FINAL DEMO

Recruiter login

↓

Create Python Developer job

↓

Candidate/resume

↓

Resume AI

↓

Match score + explanation

↓

Interview upload

↓

Transcript

↓

Interview analysis

↓

Unified report

↓

Human decision

Candidate login

↓

Interview result

↓

Feedback

↓

Improvement history

## Acceptance criteria

End-to-end workflow works.

KPI values are based on actual evidence.

AI limitations are documented.

Human-review mechanism is implemented.

Final deployment is usable for demonstration.

Phase complete when Final deployment is usable for demonstration.

# 3. Master Technical Architecture

HIRE SENSE

|

+--------------+--------------+

|                             |

RECRUITER                      CANDIDATE

|                             |

+--------------+--------------+

|

React Frontend

|

HTTPS

|

FastAPI API

+----------+----------+

|          |          |

v          v          v

PostgreSQL   File Store   AI Services

|

+------------+------------+

|            |            |

Resume       Matching     Interview

Analysis      Engine      Analysis

|            |            |

+------------+------------+

|

Unified Report

|

Human Review

|

Candidate Feedback

# 4. Database Blueprint

| Table | Main fields |
| --- | --- |
| users | id, name, email, password_hash, role, created_at |
| jobs | id, recruiter_id, title, description, experience, status |
| job_requirements | id, job_id, skill, required_level, weight |
| candidates | id, user_id, profile_json, resume_file_id |
| applications | id, job_id, candidate_id, status, created_at |
| interviews | id, application_id, media_file_id, transcript, status |
| resume_analyses | id, candidate_id, extracted_json, model_version |
| match_scores | id, application_id, overall_score, components_json, explanation |
| interview_analyses | id, interview_id, metrics_json, strengths_json, improvements_json |
| reports | id, application_id, report_json, generated_at |
| feedback | id, candidate_id, report_id, viewed_at |
| audit_logs | id, user_id, action, object_type, object_id, metadata, created_at |

User (Recruiter) 1 ─── * Job

User (Candidate) 1 ─── 1 Candidate

Job 1 ─── * Application

Candidate 1 ─── * Application

Application 1 ─── * Interview

Application 1 ─── 1 MatchScore

Application 1 ─── 1 Report

Interview 1 ─── 1 InterviewAnalysis

# 5. API Blueprint

| Method | Endpoint | Purpose |
| --- | --- | --- |
| POST | /auth/register | Create account |
| POST | /auth/login | Login |
| GET | /me | Current user |
| POST | /jobs | Create job |
| GET | /jobs | List jobs |
| GET | /jobs/{id} | Job detail |
| PUT | /jobs/{id} | Update job |
| POST | /candidates/resume | Upload/process resume |
| GET | /candidates/{id} | Candidate profile |
| POST | /applications | Create application |
| GET | /jobs/{id}/applications | Applications |
| POST | /interviews/upload | Upload interview |
| GET | /interviews/{id} | Interview status |
| GET | /interviews/{id}/transcript | Transcript |
| POST | /applications/{id}/analyze | Run analysis |
| GET | /applications/{id}/report | Unified report |
| POST | /applications/{id}/decision | Human decision |
| GET | /candidates/me/feedback | Candidate feedback |

# 6. Frontend Page Blueprint

| Role | Pages |
| --- | --- |
| Public | Landing, Login, Register |
| Recruiter | Dashboard, Jobs, Create Job, Applications, Candidate Report, Comparison, Review |
| Candidate | Dashboard, Profile, Resume, Applications, Interview Upload, Interview Result, Feedback, History |
| Admin | User management, audit/log view, system health (later/limited MVP) |

# 7. Recommended Folder Structure

HireSense/

├── frontend/

│   └── src/

│       ├── components/

│       ├── pages/

│       ├── services/

│       ├── hooks/

│       └── App.jsx

├── backend/

│   └── app/

│       ├── main.py

│       ├── config.py

│       ├── database.py

│       ├── models/

│       ├── schemas/

│       ├── routes/

│       ├── services/

│       │   ├── resume_service.py

│       │   ├── matching_service.py

│       │   ├── transcription_service.py

│       │   ├── interview_service.py

│       │   └── feedback_service.py

│       └── tests/

├── ai/

│   ├── resume/

│   ├── matching/

│   ├── speech/

│   ├── interview/

│   └── evaluation/

├── data/

│   ├── resumes/

│   ├── interviews/

│   └── test_cases/

├── docs/

├── docker-compose.yml

├── .env.example

└── README.md

# 8. Development Calendar

| Period | Main work |
| --- | --- |
| 10–13 Sep | Phase 0: scope, journeys, architecture, acceptance criteria |
| 14–20 Sep | Phases 1–2: React, FastAPI, PostgreSQL, authentication |
| 21–27 Sep | Phase 3: recruiter jobs, applications, candidates |
| 28 Sep–4 Oct | Phase 4: resume extraction and structured profile |
| 5–11 Oct | Phase 5: matching + explainability |
| 12–18 Oct | Phase 6: interview upload + transcription |
| 19–25 Oct | Phases 7–9: interview intelligence + report + feedback |
| 26–31 Oct | Phase 10: testing and evaluation round 1 |
| 1–10 Nov | Phase 10–11: validation, fixes and deployment |
| 11–15 Nov | KPI/evidence freeze |
| 16–20 Nov | Phase 12: final demo + final MVP |

# 9. Responsible AI Checklist

AI is decision support, not autonomous hiring.

Final decision remains with recruiter/user.

Do not use sensitive personal characteristics as ranking criteria.

Do not use photos/names as proxies for suitability.

Do not infer personality, honesty, mental state or emotion for hiring.

Show evidence behind important scores.

Show limitations and uncertainty.

Keep original resume/transcript evidence available to authorized reviewers.

Log model/prompt/version information for reproducibility.

Test diverse cases and document failure modes.

Provide a way for human reviewers to override or challenge AI output.

# 10. Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Hallucinated resume facts | Wrong candidate profile | Schema validation + evidence checking |
| Speech recognition errors | Wrong interview analysis | Diverse test set + transcript visibility |
| Bias | Unfair evaluation | Sensitive-attribute exclusion + diverse testing |
| AI over-trust | Human decision replaced in practice | Explainability + explicit human review |
| Scope creep | MVP not finished | P0 scope freeze + defer advanced features |
| Slow processing | Poor UX | Background jobs + status states |
| Privacy breach | Candidate harm/trust loss | Authorization + secure storage + minimal logs |
| Weak validation | Unproven product | Structured interviews + pilot testing |
| Weak business model | Commercial uncertainty | Pricing/pilot discussions |

# 11. MVP Definition of Done

☐ Recruiter can register/login.

☐ Candidate can register/login.

☐ Role permissions work.

☐ Recruiter can create a job.

☐ Candidate/application can be created.

☐ Resume can be uploaded securely.

☐ Resume becomes structured data.

☐ Job–candidate match is calculated.

☐ Match explanation is visible.

☐ Interview media can be uploaded.

☐ Speech can be transcribed.

☐ Interview metrics are generated.

☐ Question-specific analysis is generated.

☐ Unified report is available.

☐ Recruiter can make a human decision.

☐ Candidate can view feedback.

☐ AI/model versions are recorded.

☐ Sensitive attributes are excluded from scoring.

☐ 50+ AI test cases are evaluated.

☐ 30+ human-vs-AI comparisons are documented.

☐ 10+ users complete prototype testing.

☐ 15+ pilot users are targeted/validated.

☐ Major usability issues are documented and addressed.

☐ Deployment is reproducible.

☐ KPI dashboard contains real evidence.

☐ Known limitations are documented.

# 12. Exact Team Execution Workflow

Freeze Phase 0 documents.

Create Git repository and assign owners.

Build frontend/backend foundation.

Build database and authentication.

Build recruiter workflow.

Add resume AI.

Add matching engine.

Add interview processing.

Add interview intelligence.

Build unified report and human review.

Build candidate feedback.

Create fixed AI evaluation dataset.

Run technical and usability tests.

Fix high-priority issues and perform second prototype iteration.

Run pilot validation and collect KPI evidence.

Deploy and prepare final demo.

One-line strategy Build the hiring workflow first → add resume intelligence → add matching → add interview intelligence → add unified report → add candidate feedback → test everything → validate with users → deploy the evidence-backed MVP.

# 13. What NOT to Build in V1

Full ATS replacement.

Automated hiring/rejection decisions.

Automated interview scheduling.

Predictive hiring analytics.

Real-time compensation intelligence.

Competitor intelligence at production scale.

Emotion/personality detection from faces or voices.

Large enterprise integrations.

These features can be considered after the core MVP is proven. The supplied roadmap emphasizes learning and validation rather than simply adding features.

# 14. Source Grounding

The supplied hiring-process document maps the recruiter journey across 20 stages and the final-year student/job-seeker journey, highlighting problems such as resume screening, candidate matching, initial screening, interview assessment, candidate comparison, shortlisting, interview performance, communication and lack of feedback.

The Week 1 audit identifies HireSense as an early concept/TRL-2 venture and highlights gaps in customer validation, technical reliability, market/competitive understanding, willingness to pay and ethical/bias safeguards.

The Week 2 roadmap sets the project around customer discovery, prototype improvement, recruiter pilot testing, technical/ethical validation, business-model validation and an evidence-backed MVP. The filled roadmap targets 20 November 2026 for final readiness, with customer interviews, prototype iterations, user tests, pilot users, KPI evidence and final demonstration.

This roadmap therefore treats software development and venture validation as parallel work: build only enough to test the most important assumptions, measure results, improve, and then freeze the MVP.